## Risk log
ID | Risk description | Project Risk | Risk Category | Likelihood of the risk occurring | Impact to the project if the risk occurs | Risk Score Rating based on impact & likelihood. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood.
1 | Property has suffered as a consequence of under investment over a considerable time | Deterioration in the fabric of the building may lead to increased refurbishment costs | Financial | Unlikely (2) | Minor (2) | 4 | Condition Survey has reported the building is in reasonable condition
2 | Drop off in cutomer base | The Vale's customer base has fallen off over the Covid period, which could result in lower than projected income levels | Financial | Remote (1) | MInimal (1) | 1 | Initial public consultations and response to survey indicates that there will be strong local support; and once owned by the community the commitment to use the pub and to encourage others to do so wil be considerable
3 | A lack of interest in the community share offer | Failure to raise sufficient funds to buy the property. | Financial | Unlikely (2) | Major (4) | 8 | Initial public consultations and response to survey indicates that there will be strong local interest; there will also be a comprehensive marketing strategy to promote the offer locally and further afield
4 | A lack of sufficient finance after purchasing the pub to complete the refurbishment and development works | Could lead to delay or change the scope of the plan and the programme | Project | Possible (3) | Major (4) | 12 | Based on initial research into grant applications we are confident that the project meets the criteria of some capital grant funds. We acknowledge a small risk that applications might not be sucessful and are ready to scale back plans and do things differently, on a longer programme utilising comunity volunteers from a pool of many who have indicated that they would be willing to donate their time and skills
5 | Covid 19 restrictions continuing or being extended, impacting on our ability to trade as forecast | Could lead to reduced number of customers allowed inside the building, leading to reduced levels of income and some higher cleaning costs | Financial | Possible (3) | Significant (3) | 9 | We anticipate the purchase of the pub being completed early in 2022; at present it is difficult to foresee the effect of the pandemic on the business operation, but based on current regulations and the success of the vaccination programme we do not envisage this to be a major risk
6 | Lack of community support, both in general and as volunteers | Lack of community support could lead to lower than planned customer based and effect projected income | Financial | Remote (1) | Significant (3) | 3 | Consultations indicate that there is significant support for the project; the Steering Group is large and ensures wide ranging community support
|  | Lack of community support could lead to fewer volunteers, resuling in reduced ability to meet some of the project aspirations | Project | Remote (1) | Significant (3) | 3 | Consultations indicate that there is significant support for the project; the Steering Group is large and ensures wide ranging community support
7 | Changes in external factors over the next three years - such as economic downturn, grant funder's policy change, unexpected competition etc | Economic downturn could lead to reduced customer numbers and reduction in income | Financial | Possible (3) | Significant (3) | 9 | An alternative, less ambitious and more affordable plan has been developed as a fall back which ensures that the key components of the project would still be achieved
|  | Change to grant finder policy could lead to grants being reduced or becoming unavailable | Funding | Possible (3) | Critial (5) | 15 | An alternative, less ambitious and more affordable plan has been developed as a fall back which ensures that the key components of the project would still be achieved; there are several grant streams available at this time and it is unlikely that all will be 'pulled' alltogether
|  | New competition could lead to reduced customer numbers and reduction in income | Financial | Unlikely (2) | MInimal (1) | 2 | Many local pubs continue to close and are unlikely to reopen and there is strong demand from local residents and visitors for a good quality pub with food
8 | Failure to appoint and retain suitably qualified key personnel, especially Manager and/or Chef | Could lead to disruption to the business leading to a loss of income | Financial | Possible (3) | Minor (2) | 6 | A robust HR recruitment process will be established; and the possibility of appointing part time staff to job share should be considered, providing greater flexibility and resilience. Should Manager leave unexpectedly then the dat to day management role would be undertaken by committee members with greater use of casual bar/kitchen staff until a replacement could be found
9 | Failure to achieve and maintain a correct balance between quality/ value/ profit | Could lead to pore reputation and a reduction in customer base, leading to a reduction in income | Financial | Possible (3) | Minor (2) | 6 | Quality and value for money, as well as strong fiscal mamagement have to be the cornerstone of the project; the committee is committed to establishing high standards of service and offer to ensure customer satisfaction and to build a good reputation
Impact Definition
Minimal - effect on Finance<£10k or on Programme < month
Minor - effect on Finance >£10k <£30k or Programme >1m <3m
Significant - effect on Finance >£30k <£50k or Programme >3m <6m
Major - effect on Finance >£50k <£100k or Programme >6m <12m
Critical- effect on Finance >£100k or Programme <12m
| Risk |  |  | Impact
| Likelihood | Minimal (1) | Minor (2) | Significant (3) | Major (4) | Critical (5)
| Almost Certain (5) | 5 | 10 | 15 | 20 | 25
| Likely (4) | 4 | 8 | 12 | 16 | 20
| Possible (3) | 3 | 6 | 9 | 12 | 15
| Unlikely (2) | 2 | 4 | 6 | 8 | 10
| Remote (1) | 1 | 2 | 3 | 4 | 5

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low